## Action Plan
Priority | Phase | Activity | Details
P1 | Identity | Enable Azure AD / Entra ID Integration | SSO, Azure RBAC, MFA, PIM
P1 | Security | Deploy Azure Firewall Premium | Ingress/Egress filtering and inspection
P1 | Ingress | Deploy Application Gateway WAF | WAF v2 with AGIC integration
P1 | AKS | Harden AKS Cluster | Private AKS, Policy, Defender, Workload Identity
P1 | Access | Move Jump Server Behind Azure Bastion | Remove public SSH exposure
P2 | Storage | Enable Private Endpoint for Blob Storage | Disable public access
P2 | Registry | Enable Private Endpoint for ACR | Private image pulls from AKS
P2 | Network | Implement Hub-Spoke Architecture | Segmentation and centralized security
P2 | Monitoring | Enable Defender for Cloud | Threat detection and compliance
P3 | DR | Deploy DR Region | Business continuity
P3 | Registry | Enable ACR Geo-Replication | Multi-region image availability
P3 | Backup | Enable Storage GRS & Backup | Disaster recovery readiness

## Target Architecture
Component | Recommendation
AKS | Private AKS Cluster
Ingress | Application Gateway WAF v2 + AGIC
Firewall | Azure Firewall Premium
Identity | Azure AD / Entra ID Integration
Container Registry | ACR with Private Endpoint
Storage | Blob Storage with Private Endpoint
Admin Access | Azure Bastion / Hardened Jump Server
Monitoring | Azure Monitor + Defender for Cloud